## Sample Size Calculator
MORTALITY SURVEY SAMPLE SIZE CALCULATOR
PARAMETER | VALUE | GUIDANCE
Expected CDR (/10,000/day) | 0.5 | Baseline sub-Saharan Africa: ~0.5
Desired precision (+/-) | 0.3 | Typically 0.3-0.5
Recall period (days) | 90 | Standard: 90 days
Average household size | 5 | Typically 4-7
Design effect (DEFF) | 2 | Typical: 1.5-2.0
Non-response rate (%) | 10 | Typically 5-10%
Number of clusters | 25 | Standard: 25-30
CALCULATION
Daily rate
Z-alpha (95%) | 1.96
Variance numerator
Precision squared
SRS person-days needed
SRS persons needed
Cluster-adjusted persons
After non-response
Total households needed
Households per cluster
FINAL: Total households
REFERENCE
CDR emergency threshold: 1.0 / 10,000 / day
U5DR emergency threshold: 2.0 / 10,000 / day

## Fieldwork Planning
FIELDWORK TEAM PLANNING
Converts sample size into enumerator teams, supervisors, and fieldwork duration
PARAMETER | VALUE | GUIDANCE
Interviews per enumerator per day | 5 | Mortality surveys: 4-6/day. Depends on terrain, density, interview length (~30-45 min).
Travel days between clusters | 1 | 0.5 if close; 1-2 in dispersed, conflict-affected or mountainous settings.
Enumerators per team | 4 | 4-6 per team. Larger teams finish faster but harder to supervise and transport.
Supervisor ratio (enum per supervisor) | 4 | 1 supervisor per 4-6 enumerators. Supervisors run quality checks and community entry.
Number of field teams | 2 | More teams = shorter fieldwork, higher cost. 2-3 teams is typical.
Training days | 3 | 3 days for enumerator training. Add 1-2 days for pilot testing.
Buffer days (weather, access, rest) | 2 | Rain, road closures, security incidents, rest days. 1-3 depending on context.
LINKED FROM SAMPLE SIZE
Number of clusters
Households per cluster
Total households
FIELDWORK CALCULATION
Data collection days per cluster |  | HH per cluster / (enumerators x interviews/day)
Clusters per team |  | Total clusters / number of teams
Field days per team |  | Collection days + travel between clusters
Total enumerators |  | Enumerators per team x teams
Supervisors needed |  | Total enumerators / supervisor ratio
Total field staff |  | Enumerators + supervisors
Data collection duration (days) |  | Longest team determines duration
Training
Buffer
TOTAL FIELDWORK DURATION (days)
Approximate weeks
LOGISTICS CHECKLIST
[ ] Vehicles: 1 per team (with drivers)
[ ] Tablets/phones: 1 per enumerator, loaded with XLSForm
[ ] Supervisor kits: daily data quality checklists, cluster maps
[ ] Enumerator kits: ID badge, consent forms, referral cards, pens
[ ] Per diem: all field staff x field days
[ ] Fuel and vehicle maintenance budget
[ ] Communication: airtime for all field staff
[ ] Data backup: portable power banks, Wi-Fi/cellular coverage plan